## Anskaffelser Legemidler
Oppdatert 23. mars 2026
Anskaffelse ID | Anskaffelsenavn | Prosjektleder | Fagrådgiver | Prosjektstart/ Estimert prosjektstart | Kunngjøring/ Estimert kunngjøring | Tildeling/ Estimert tildeling | Avtalestart
2632a | 2632a Everolimus og Mykofenolsyre (enterotablett) | Lars Hjellup | Synne Ildahl Svendsen | 2025-05-23 | 2025-06-24 | 2025-10-09 | 2026-04-01
2607a | 2607a JAK hemmere | Piv Rivenæs | Helle Nærsnes Endresen | 2025-06-26 | 2025-10-16 | 2025-12-01 | 2026-04-01
2632 | 2632 Transplantasjon | Lars Hjellup | Synne Ildahl Svendsen | 2024-10-15 | 2025-03-31 | 2025-12-03 | 2026-04-01 02:00
2609a | 2609a Veksthormonmangel | Beate Bjørnstad Løkke | Therese Velle | 2025-04-01 | 2025-10-06 | 2025-12-05 | 2026-05-01
2699b | 2699b Fabry sykdom | Beate Bjørnstad Løkke | Martin Haugrud Kastnes | 2025-03-10 | 2025-08-28 | 2025-10-24 | 2026-05-01
2699l | 2699l ITP | Piv Rivenæs | Helle Nærsnes Endresen | 2025-01-27 01:00 | 2025-09-17 | 2025-10-31 | 2026-05-01 02:00
2699g | 2699g Sjeldne sykdommer | Piv Rivenæs | Synne Ildahl Svendsen | 2025-05-01 | 2025-08-27 | 2025-10-28 | 2026-05-01 02:00
2599r | 2699r Hjerteamyloidose | Beate Bjørnstad Løkke | Synne Ildahl Svendsen | 2025-05-23 | 2026-02-09 | 2026-03-17 | 2026-07-01
2667 | 2667 Hepatitt B vaksine | Beate Bjørnstad Løkke | Tonje Marie Lukkassen | 2025-05-23 | 2025-10-24 | 2025-12-17 | 2026-07-01
2699f | 2699f Progressiv fibroserende interstitiell lungesykdom | Piv Rivenæs | Tonje Marie Lukkassen | 2025-05-06 | 2026-03-03 | 2026-04-17 | 2026-07-01
2612 | 2612 Blodkoagulasjonsfaktorer | Lars Hjellup | Erik Hviding | 2025-05-05 | 2025-12-08 | 2026-02-04 | 2026-09-01
2699j | 2699j Wilsons sykdom | Tor Egil Frostelid | Martin Haugrud Kastnes | 2025-01-20 01:00 | 2025-10-01 02:00 | 2026-01-06 01:00 | 2026-09-01 02:00
2617 | 2617 Parkinson | Eirik Sverrisson | Anne Helen Ognøy | 2025-12-15 01:00 | 2026-04-17 02:00 | 2026-06-18 02:00 | 2026-09-01 02:00
2616 | 2616 Alvorlig astma og KOLS | Tor Egil Frostelid | Synne Ildahl Svendsen | 2025-04-03 02:00 | 2026-03-03 01:00 | 2026-04-30 02:00 | 2026-09-01 02:00
2668 | 2668 Rotavirus vaksine | Beate Bjørnstad Løkke | Therese Velle | 2025-10-02 | 2026-01-29 | 2026-04-08 | 2026-10-01
2607gj-1 | 2607gj pazopanib | Eirik Sverrisson | Martin Haugrud Kastnes | 2025-11-03 01:00 | 2026-01-08 01:00 | 2026-03-20 01:00 | 2026-10-01 02:00
2607 | 2607 Onkologi (patentert) | Piv Rivenæs | Martin Haugrud Kastnes | 2025-08-29 | 2026-01-23 | 2026-03-24 | 2026-10-01 02:00
2624 | 2624b Radiofarmaka | Lars Hjellup | Martin Haugrud Kastnes | 2025-09-17 02:00 | 2026-03-27 | 2026-06-03 | 2026-11-15 01:00
2661 | 2661 Sesonginfluensavaksiner | Lars Hjellup | Tonje Marie Lukkassen | 2026-01-14 | 2026-06-26 | 2026-09-23 | 2026-12-15
2706b | 2706b TNF BIO uten biotilsvarende konkurranse | Beate Bjørnstad Løkke | Synne Ildahl Svendsen | 2026-02-23 | 2026-08-28 | 2026-10-30 | 2027-02-01
2714a | 2714a seleksipag (PAH) | Piv Rivenæs | Synne Ildahl Svendsen | 2026-03-27 | 2026-04-21 | 2026-06-11 | 2027-02-01
2703 | 2703 Infusjons- og skyllevæsker | Beate Bjørnstad Løkke | Monica Eitran | 2025-03-27 | 2025-10-13 | 2026-03-06 | 2027-02-01
2701h | 2701h klorheksidin | Eirik Sverrisson | Monica Eitran | 2026-03-13 01:00 | 2026-05-15 02:00 | 2026-06-26 02:00 | 2027-04-01 02:00
2799a | 2799a HAE | Lars Hjellup | Martin Haugrud Kastnes | 2026-04-22 | 2026-08-27 | 2026-10-15 | 2027-05-01
2704 | 2704 Sondeernæring og andre medisinske næringsmidler | Tor Egil Frostelid | Monica Eitran | 2025-05-13 | 2026-04-10 | 2026-06-26 | 2027-05-01
2705 | 2705 MS | Eirik Sverrisson | Anne Helen Ognøy | 2026-03-04 01:00 | 2026-06-18 02:00 | 2026-10-01 02:00 | 2027-05-01 02:00
2722 | 2722 Plasmaderiverte legemidler | Piv Rivenæs | Erik Hviding | 2025-11-03 | 2026-02-26 | 2026-04-24 | 2027-06-01
2730 | 2730 CKD | Tor Egil Frostelid | Anne Helen Ognøy | 2026-04-22 | 2026-09-07 | 2026-11-02 | 2027-06-01
2707 | 2707 Onkologi | Piv Rivenæs | Martin Haugrud Kastnes | 2026-08-13 | 2027-01-21 | 2027-03-24 | 2027-10-01
2707gj | 2707gj Onkologi ikke patentert | Eirik Sverrisson | Martin Haugrud Kastnes | 2025-01-16 01:00 | 2026-03-06 01:00 | 2026-10-01 02:00 | 2027-10-01 02:00
2713 | 2713 LAR | Lars Hjellup | Erik Hviding | 2026-08-20 | 2026-10-27 | 2027-01-08 | 2027-11-01
2814 | 2814 PAH | Piv Rivenæs | Synne Ildahl Svendsen | 2027-01-06 | 2027-04-14 | 2027-06-03 | 2028-02-01
2802 | 2802 Kontrastmidler | Tor Egil Frostelid | Monica Eitran | 2026-05-01 | 2027-01-15 | 2027-05-01 | 2028-02-01
2801b | 2801b Legemidler ikke inf inj | Eirik Sverrisson | Maja Monsen | 2025-01-30 01:00 | 2027-02-26 01:00 | 2027-06-04 02:00 | 2028-02-01 01:00
2801c | 2801c Legem infusjon injeksjon | Eirik Sverrisson | Maja Monsen | 2025-01-03 01:00 | 2026-06-19 02:00 | 2027-02-12 01:00 | 2028-02-01 01:00
2801a | 2801a Antiinfektiva legemidler 2801a | Eirik Sverrisson | Maja Monsen | 2024-11-29 01:00 | 2026-11-02 01:00 | 2027-04-01 02:00 | 2028-04-01 02:00

## hiddenSheet (hidden)
shi_procurement:rVkS+iWUCgTf3WEvBnJvUHQY217/VoqDriNSd1a1DiYZaR5zRlCPyKYmjXg/e/pvuBbpKroogl40C11DQGphgg==:shi_procurementid=%28Ikke%20endre%29Anskaffelse&checksumLogicalName=%28Ikke%20endre%29Radkontrollsum&modifiedon=%28Ikke%20endre%29Endret%20den&shi_procurement_id=Anskaffelse%20ID&shi_procurement_name=Anskaffelsenavn&shi_sakarkivnummer=Arkiv%20nummer&shi_division_unit=Divisjons%20Enhet&ownerid=Eier&shi_subject_advisor=Fagr%c3%a5dgiver&shi_jurist=Jurist&shi_procurementstatus=Anskaffelsesstatus&shi_milestone_choice=Milep%c3%a6l%20valg&shi_project_start_planned=Prosjektstart%20planlagt&shi_project_start_revised=Prosjektstart%20revidert&shi_project_start_completed=Prosjektstart%20utf%c3%b8rt&shi_tender_published_planned=Kunngj%c3%b8ring%20planlagt&shi_tender_published_revised=Kunngj%c3%b8ring%20revidert&shi_tender_published_completed=Kunngj%c3%b8ring%20utf%c3%b8rt&shi_estimated_contract_award_date=Avtale%20tildelt%20planlagt&shi_contract_award_date_revised=Avtale%20tildelt%20revidert&shi_actual_contract_award_date=Avtale%20tildelt%20utf%c3%b8rt&shi_estimated_complete_date=Klar%20for%20implementering%20planlagt&shi_complete_date_revised=Klar%20for%20implementering%20revidert&shi_actual_complete_date=Klar%20for%20implementering%20utf%c3%b8rt&shi_contract_valid_from_planned=Virkningsdato%20planlagt&shi_contract_valid_from_revised=Virkningsdato%20revidert&shi_contract_valid_from_completed=Virkningsdato%20utf%c3%b8rt&shi_contract_length_months=Avtalelengde%20i%20m%c3%a5neder&shi_expected_volume=%c3%85rlig%20verdi%20estimert&shi_volume_revised=%c3%85rlig%20verdi%20revidert&shi_return=Gevinst&shi_aggregertrisikovurdering=Aggregert%20risikovurdering&747cbce0-8f50-4b47-9c5c-3bdcae6c9561.shi_confirmedstep=Bekreftet%20steg%20%28Gevinst%29%20%28Gevinstberegning%29&10211117-29f5-448b-9655-2bb4e731a038.shi_risikoniva=Risikoniv%c3%a5%20%28Aggregert%20risikovurdering%29%20%28Risikovurdering%29
Ikke startet | Pågår | Avsluttet | Avlyst
Ikke startet | Prosjektoppstart | Kunngjøring | Avtale tildelt | Avtale signert og klar til implementering | Virkningsdato | Avsluttet | Avlyst
Ikke bekreftet | Steg 1 bekreftet | Steg 2 bekreftet | Steg 1 og 2 bekreftet