## 03 09 2026
Oppdatert: 3. september 2026
Anskaffelse ID | Anskaffelsenavn | Anskaffelsesstatus | Prosjektleder | Fagrådgiver | Prosjektstart/ Estimert prosjektstart | Kunngjøring/ Estimert kunngjøring | Tilbudsfrist planlagt | Kontrakt gyldig fra planlagt
2607 | Onkologi | Pågår | Piv Rivenæs | Hanne Maria Holm / Martin Haugrud Kastnes | 2025-08-28 02:00 | 2026-01-22 01:00 | 2026-03-11 01:00 | 2026-10-01 02:00
2617 | Parkinson | Pågår | Eirik Sverrisson | Anne Helen Ognøy | 2025-12-15 01:00 | 2026-05-28 02:00 | 2026-08-28 02:00 | 2026-11-01 01:00
2624b | Radiofarmaka | Pågår | Lars Hjellup | Martin Haugrud Kastnes | 2025-09-17 02:00 | 2026-03-30 02:00 | 2026-05-21 02:00 | 2026-11-15 01:00
2661 | Sesonginfluensavaksiner | Pågår | Lars Hjellup | Tonje Marie Lukkassen | 2026-01-14 01:00 | 2026-06-24 02:00 | 2026-08-26 02:00 | 2026-12-15 01:00
2670 | Covid-19 vaksiner | Pågår | Tor Egil Frostelid | Therese Velle / Synne Ildahl Svendsen | 2026-04-15 02:00 | 2026-08-21 02:00 | 2026-09-30 02:00 | 2027-01-01
2703 | Infusjons- og skyllevæsker | Pågår | Beate Bjørnstad Løkke | Monica Eitran | 2025-03-26 01:00 | 2025-10-12 02:00 | 2025-11-27 01:00 | 2027-02-01
2661a | RHF sesonginfluensavaksine | Pågår | Lars Hjellup | Tonje Marie Lukkassen | 2026-03-18 01:00 | 2026-10-14 02:00 | 2026-11-18 02:00 | 2027-02-01 01:00
2706b | TNF BIO uten biotilsvarende konkurranse | Pågår | Beate Bjørnstad Løkke | Synne Ildahl Svendsen | 2026-02-22 01:00 | 2026-08-26 02:00 | 2026-10-06 02:00 | 2027-02-01 01:00
2701h | Klorheksidin | Pågår | Eirik Sverrisson | Monica Eitran | 2026-03-13 01:00 | 2026-05-15 02:00 | 2026-05-29 02:00 | 2027-04-01 02:00
2704 | Sondeernæring og andre medisinske næringsmidler | Pågår | Tor Egil Frostelid | Monica Eitran | 2025-08-01 02:00 | 2026-04-15 | 2026-06-01 02:00 | 2027-05-01
2799a | HAE | Pågår | Lars Hjellup | Martin Haugrud Kastnes | 2026-04-22 02:00 | 2026-08-26 02:00 | 2026-10-01 02:00 | 2027-05-01 02:00
2799m | Ivakaftor | Pågår | Piv Rivenæs | Synne Ildahl Svendsen | 2026-08-10 02:00 | 2026-09-22 02:00 | 2026-10-28 01:00 | 2027-05-01 02:00
2722 | Plasmaderiverte legemidler | Pågår | Piv Rivenæs | Erik Hviding | 2025-11-02 01:00 | 2026-02-25 01:00 | 2026-05-06 02:00 | 2027-05-31 02:00
2730 | CKD | Pågår | Tor Egil Frostelid | Anne Helen Ognøy | 2026-04-22 02:00 | 2026-09-08 | 2026-10-12 02:00 | 2027-06-01 02:00
2799k | ATC gruppe A16AX08 (teduglutid) | Pågår | Piv Rivenæs | Synne Ildahl Svendsen | 2026-08-12 02:00 | 2026-10-20 02:00 | 2026-11-26 01:00 | 2027-09-01 02:00
2707 | Onkologi | Pågår | Piv Rivenæs | Hanne Maria Holm / Martin Haugrud Kastnes | 2026-08-12 02:00 | 2027-01-29 01:00 | 2027-03-11 01:00 | 2027-10-01 02:00
2707gj | Onkologi ikke patentert | Pågår | Eirik Sverrisson | Martin Haugrud Kastnes | 2025-01-16 01:00 | 2026-03-06 01:00 | 2026-04-30 02:00 | 2027-10-01 02:00
2713 | LAR | Pågår | Lars Hjellup | Erik Hviding | 2026-06-16 02:00 | 2026-10-15 02:00 | 2026-11-19 01:00 | 2027-11-01 01:00
2802 | Kontrastmidler | Pågår | Tor Egil Frostelid | Monica Eitran | 2026-06-01 | 2027-01-10 | 2027-02-10 | 2028-02-01
2806b | TNF BIO uten biotilsvarende konkurranse | Ikke startet | Beate Bjørnstad Løkke | Synne Ildahl Svendsen | 2027-02-23 | 2027-08-28 | 2027-10-06 | 2028-02-01
2806a | TNF BIO med biotilsvarende konkurranse | Pågår | Beate Bjørnstad Løkke | Lilly Shi | 2026-08-03 02:00 | 2027-02-25 01:00 | 2027-04-08 02:00 | 2028-02-01 01:00
2814 | PAH | Ikke startet | Piv Rivenæs | Synne Ildahl Svendsen | 2027-01-05 01:00 | 2027-04-13 02:00 | 2027-05-19 02:00 | 2028-02-01 01:00
2801b | Legemidler ikke inf inj | Pågår | Eirik Sverrisson | Maja Monsen | 2025-01-30 01:00 | 2027-02-26 01:00 | 2027-04-30 02:00 | 2028-02-01 01:00
2801c | Legemidler infusjon injeksjon | Pågår | Eirik Sverrisson | Maja Monsen | 2025-03-12 01:00 | 2026-06-26 02:00 | 2026-09-18 02:00 | 2028-02-01 01:00
2801a | Antiinfektiva legemidler 2801a | Pågår | Eirik Sverrisson | Maja Monsen | 2024-11-29 01:00 | 2026-11-02 01:00 | 2027-01-08 01:00 | 2028-04-01 02:00
2805 | MS | Pågår | Eirik Sverrisson | Anne Helen Ognøy | 2026-03-04 01:00 | 2027-05-03 02:00 | 2027-09-16 02:00 | 2028-05-01 02:00

## hiddenSheet (hidden)
shi_procurement:6h0wKdoq29msJZFV4dicvP2uSvUGURImvjOq34NmqBWyeoTvDvzaGsoTlCSlhrZkYY9CW+RQtItUMG689gsqvA==:shi_procurementid=%28Ikke%20endre%29Anskaffelse&checksumLogicalName=%28Ikke%20endre%29Radkontrollsum&modifiedon=%28Ikke%20endre%29Endret%20den&shi_procurement_name=Anskaffelsenavn&shi_procurement_id=Anskaffelse%20ID&shi_national_category=Nasjonal%20kategori&shi_procurementstatus=Anskaffelsesstatus&shi_project_manager_lookup=prosjektleder&shi_subject_advisor=Fagr%c3%a5dgiver&shi_case_number=Hoved%20Sak&shi_sakarkivnummer=Arkiv%20nummer&shi_project_start_planned=Prosjektstart%20planlagt&shi_project_start_revised=Prosjektstart%20revidert&shi_project_start_completed=Prosjektstart%20utf%c3%b8rt&shi_tender_published_planned=Kunngj%c3%b8ring%20planlagt&shi_tender_published_revised=Kunngj%c3%b8ring%20revidert&shi_tender_published_completed=Kunngj%c3%b8ring%20utf%c3%b8rt&shi_tender_deadline_planned=Tilbudsfrist%20planlagt&shi_tender_deadline_revised=Tilbudsfrist%20revidert&shi_tender_deadline_completed=Tilbudsfrist%20utf%c3%b8rt&shi_estimated_contract_award_date=Avtale%20tildelt%20planlagt&shi_contract_award_date_revised=Avtale%20tildelt%20revidert&shi_actual_contract_award_date=Avtale%20tildelt%20utf%c3%b8rt&shi_estimated_complete_date=Klar%20for%20implementering%20planlagt&shi_complete_date_revised=Klar%20for%20implementering%20revidert&shi_actual_complete_date=Klar%20for%20implementering%20utf%c3%b8rt&shi_contract_valid_from_planned=Kontrakt%20gyldig%20fra%20planlagt&shi_contract_valid_from_revised=Kontrakt%20gyldig%20fra%20revidert&shi_contract_valid_from_completed=Kontrakt%20gyldig%20fra%20utf%c3%b8rt
Ikke startet | Pågår | Avsluttet | Avlyst